## Product Committee review of tas
Issue Type | Issue key | Issue id | Parent id | Summary | Assignee | Assignee Id | Reporter | Reporter Id | Priority | Status | Resolution | Created | Updated | Due date | Custom field (Customer) | Original estimate | Sprint | Sprint_1 | Sprint_2 | Sprint_3 | Sprint_4
Improvement | BSPLMAX-2508 |  | 20-10-2022 00:00:00 | ECO Sub-workflow data for email templates. | Jeppe Just Svendsen | 612e36d845cd76006a8913cd | Søren Christensen | 557058:20f5eea0-01b1-45e4-a7cd-fcbfbdf941b8 | Medium | Open |  | 25-01-2023 16:31:00 | 25-01-2023 16:31:00 | sdfsd | Stein-Industries
Bug2 | BSPLMAX-2507 |  |  | sdasdin ECO Template is not copied over in the vault and can't be opened in new ECOs | Jeppe Just Svendsen | 612e36d845cd76006a8913cd | Joachim Thygesen | 60c7570e2bd2140069c01d5f | High | Internal approval |  | xxx |  |  | Stein-Industries |  | CR Sprint Week 3-4
Task | CAD-915 | 23681 |  | Setup form - for CAD configurator | Bjarne Mortensen | 557058:0534088c-1ed7-4fd0-9fb8-c6c81d5e944f | Jesper B. Thomsen | 5bed6d00db82d4090ba69168 | Medium | Estimate |  | 2023-01-26 10:57 | 2023-01-27 09:06 |  | PDM
Task | Task | CAD-914 |  |  | Divide responsiblility of core areas | Bjarne Mortensen | 557058:0534088c-1ed7-4fd0-9fb8-c6c81d5e944f | Jesper B. Thomsen | 5bed6d00db82d4090ba69168 | Medium | Estimate |  | 2023-01-26 10:40 | 2023-01-26 10:46 |  | PDM
New Feature | CAD-913 | 23679 |  | Documentation CAD configuration | Jakub Szkandera | 5d6e060b8f0aa30dba0b00f6 | Jesper B. Thomsen | 5bed6d00db82d4090ba69168 | Medium | Estimate |  | 2023-01-26 10:35 | 2023-01-26 13:01 |  | PDM
Improvement | BSPLMAX-2514 | 23699 |  | German translation of Bluestar Configurator | Hamid Keshmiri Neghab | 629f0156e318a50069375bd6 | Johannes Bach Larsen | 62306f53867a4e0070959c67 | Medium | Estimate |  | 2023-01-27 11:33 | 2023-01-27 21:01 |  | PDM
Improvement | BSCFG-279 | 23615 |  | CFG - Expand / Collapse all groups | Jakub Szkandera | 5d6e060b8f0aa30dba0b00f6 | Jakub Szkandera | 5d6e060b8f0aa30dba0b00f6 | Medium | Stakeholder Sign-off |  | 2023-01-23 07:32 | 2023-01-30 08:02 |  | PDM | 7200 | PD23 Week 1-3
Bug | BSPLMAX-2500 | 23628 |  | Compliance - Wrong color and Display Results Not working for Manu item | Zhiru Cao | 612e36daa0dfd100689711ce | Joachim Thygesen | 60c7570e2bd2140069c01d5f | Medium | Technical Review |  | 2023-01-23 15:09 | 2023-01-27 22:01 |  | NKT | 23400 | CR Sprint Week 3-4
Bug | BSPLMAX-2506 | 23664 |  | Spelling mistake in the bluestar setup | Zhiru Cao | 612e36daa0dfd100689711ce | Casper Fløe Mikkelsen | 633aa3362eaaa5dcfa162ec9 | Medium | Internal approval |  | 2023-01-25 13:57 | 2023-01-30 08:37 |  | Motus | 7200 | CR Sprint Week 5-6
Bug | CAD-911 | 23657 |  | SE - Drag drop parts in assembly is not working | Jakub Szkandera | 5d6e060b8f0aa30dba0b00f6 | swati amol dhere | 6192355bc15977006af40c1c | Low | Estimate |  | 2023-01-25 09:30 | 2023-01-25 10:15 |  | Lesker
Bug | CAD-912 | 23663 |  | Check in dialog show properties for object name and allow change of it | Bjarne Mortensen | 557058:0534088c-1ed7-4fd0-9fb8-c6c81d5e944f | Jesper B. Thomsen | 5bed6d00db82d4090ba69168 | Medium | Estimate |  | 2023-01-25 13:39 | 2023-01-25 13:40 |  | Houno
Bug | BSPLMAX-2513 | 23694 |  | Copy Workflow Menu is not enabled as a role in BLuestar PLM - Admin | Per Nielsen | 5f9bc93081b2880078c8e8b3 | Rick Trask | 5ede4ba896beaa0aaef74e58 | Medium | Open |  | 2023-01-26 22:52 | 2023-01-26 22:58 |  | Hooker
Bug | BSPLMAX-2505 | 23662 |  | Replace function in ECO not working | Mads Kammer Christensen | 5dbae04cfc11e40c2ff429e0 | swati amol dhere | 6192355bc15977006af40c1c | Medium | Estimate |  | 2023-01-25 13:28 | 2023-01-25 21:00 |  | HighRes
Bug | BSPLMAX-2504 | 23661 |  | Description field showing text when value is empty | Jeppe Just Svendsen | 612e36d845cd76006a8913cd | Søren Christensen | 557058:20f5eea0-01b1-45e4-a7cd-fcbfbdf941b8 | Medium | Internal approval |  | 2023-01-25 13:13 | 2023-01-25 22:01 |  | Haworth | 9000 | CR Sprint Week 3-4
Bug | BSPLMAX-2503 | 23647 |  | When exporting a excel sheet from Upload table with a Class and same attribute we are not getting the full value list out | Mads Kammer Christensen | 5dbae04cfc11e40c2ff429e0 | Niels K. Markussen | 5e285375a09c140c9cc08e0e | Highest | Ready For Dev |  | 2023-01-24 15:28 | 2023-01-30 09:39 |  | Hager | 14400 | CR Sprint Week 5-6
Bug | BSPLMAX-2502 | 23645 |  | Formulas converted to BOMs when using the import BOM option with the upload tool | Mads Kammer Christensen | 5dbae04cfc11e40c2ff429e0 | Henrik Bak Kolstrup | 5e30414300bfa60ca693f82b | Highest | Stakeholder Sign-off |  | 2023-01-24 15:12 | 2023-01-30 09:41 |  | EastMetal | 14400 | CR Sprint Week 3-4
Sub-task | CAD-916 | 23698 |  | 50420/CREO Resolve dimensions using raw material unit | Bjarne Mortensen | 557058:0534088c-1ed7-4fd0-9fb8-c6c81d5e944f | Bjarne Mortensen | 557058:0534088c-1ed7-4fd0-9fb8-c6c81d5e944f | Medium | Stakeholder Sign-off |  | 2023-01-27 09:29 | 2023-01-30 09:27 |  | DAS | 1800 | PD Sprint Week 26-27 | PD Sprint Week 31-32 | PD Sprint Week 33-34 | PD Sprint Week 35-36 | PD Sprint Week 37-38
Bug | BSPLMAX-2515 | 23700 |  | Bug 81593: Copy function out of Creo generates Error message | Bjarne Mortensen | 557058:0534088c-1ed7-4fd0-9fb8-c6c81d5e944f | Jesper B. Thomsen | 5bed6d00db82d4090ba69168 | High | Estimate Ready |  | 2023-01-27 13:25 | 2023-01-30 09:16 | 2023-02-10 | DAS | 14400
Bug | BSPLMAX-2510 | 23684 |  | Create New - Select Class - Long classname, cant see select | Jeppe Just Svendsen | 612e36d845cd76006a8913cd | Søren Christensen | 557058:20f5eea0-01b1-45e4-a7cd-fcbfbdf941b8 | Medium | Estimate |  | 2023-01-26 13:35 | 2023-01-30 09:51 |  | Benning
Task | SWRD-593 | 23619 |  | Research on ECHA - procedures for submission and approval from the user side | Simon Als Nielsen | 637760d99341d1f136048795 | Simon Als Nielsen | 637760d99341d1f136048795 | Medium | In Progress |  | 2023-01-23 10:04 | 2023-01-23 10:55 |  | PDM
Change Request | STEINSW-17 | 23672 |  | ECO Sub-workflow email | Jeppe Just Svendsen | 612e36d845cd76006a8913cd | Søren Christensen | 557058:20f5eea0-01b1-45e4-a7cd-fcbfbdf941b8 | Medium | Open |  | 2023-01-25 16:23 | 2023-01-25 16:31 |  | Stein-Industries
Change Request | ROTORKSW-426 | 23682 |  | Enable CM-analyze to pick up soft-linked items. | Mads Kammer Christensen | 5dbae04cfc11e40c2ff429e0 | Abdul Aden | 6218a6bec34549007198f4f8 | High | In Progress |  | 2023-01-26 12:57 | 2023-01-30 09:32 |  | Rotork | 14400 | CR Sprint Week 3-4
Change Request | PJTRAILSW-3 | 23665 |  | Email Task Template to be Added at the Task Level (currently on the workflow only)-estimation only | Jeppe Just Svendsen | 612e36d845cd76006a8913cd | Tina Trutschel | 6321bfe5d1b3f6489b935228 | Medium | Estimate Ready |  | 2023-01-25 14:00 | 2023-01-26 22:01 |  | PJ Trailers | 7200
Bug | NORICANSW-191 | 23703 |  | Catia CGR handling | Janna Ishøy | 623da15aee1b5a00702a0719 | Bjarne Mortensen | 557058:0534088c-1ed7-4fd0-9fb8-c6c81d5e944f | Medium | Stakeholder Sign-off |  | 2023-01-27 15:02 | 2023-01-30 09:26 |  | Norican | 21600 | PD23 Week 4-5
Change Request | NORICANSW-190 | 23697 |  | 008764 email separator for multiple recipients in transfer tool | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | High | Stakeholder Sign-off |  | 2023-01-27 09:19 | 2023-01-27 22:01 |  | Norican | 7200 | PD23 Week 4-5
Change Request | NORICANSW-189 | 23696 |  | 008762 AX templates message | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | High | Stakeholder Sign-off |  | 2023-01-27 09:16 | 2023-01-27 22:01 |  | Norican | 7200 | PD23 Week 4-5
Change Request | NORICANSW-188 | 23695 |  | 008758 Release is changing BlueStar BOMUNITID | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Highest | Stakeholder Sign-off |  | 2023-01-27 09:13 | 2023-01-27 22:01 |  | Norican | 7200 | PD23 Week 4-5
Change Request | NORICANSW-187 | 23656 |  | 008743 ECO numbers not shown correctly | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Medium | Estimate |  | 2023-01-25 09:06 | 2023-01-30 09:07 |  | Norican | 18000 | PD23 Week 4-5
Change Request | NORICANSW-186 | 23653 |  | 008749 Classification name length | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Medium | Ready For Dev |  | 2023-01-24 16:03 | 2023-01-24 16:04 |  | Norican | 14400 | PD23 Week 4-5
Change Request | NORICANSW-185 | 23652 |  | 008744 LOB not possible to edit | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Medium | Ready For Dev |  | 2023-01-24 15:58 | 2023-01-27 08:59 |  | Norican | 7200 | PD23 Week 4-5
Change Request | NORICANSW-184 | 23651 |  | 008738 Issue with Item text and Release to AX | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Highest | Stakeholder Sign-off |  | 2023-01-24 15:56 | 2023-01-27 09:05 |  | Norican | 14400 | PD23 Week 4-5
Change Request | NORICANSW-183 | 23650 |  | 008735 Area Data Transfer Tool issue | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Medium | Open |  | 2023-01-24 15:51 | 2023-01-24 15:51 |  | Norican |  | PD23 Week 4-5
Change Request | NORICANSW-181 | 23648 |  | 008747 release issues BOM lines with ID containing - | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Highest | Stakeholder Sign-off |  | 2023-01-24 15:39 | 2023-01-27 09:01 |  | Norican | 18000 | PD23 Week 4-5
Task | NORICANSW-180 | 23646 |  | CFG - Workshop in CPH | Jakub Szkandera | 5d6e060b8f0aa30dba0b00f6 | Jakub Szkandera | 5d6e060b8f0aa30dba0b00f6 | Medium | Open |  | 2023-01-24 15:15 | 2023-01-30 08:03 |  | Norican |  | PD23 Week 4-5
Change Request | NORICANSW-179 | 23642 |  | Norican: Preview extract | Bjarne Mortensen | 557058:0534088c-1ed7-4fd0-9fb8-c6c81d5e944f | Bjarne Mortensen | 557058:0534088c-1ed7-4fd0-9fb8-c6c81d5e944f | Medium | Open |  | 2023-01-24 13:19 | 2023-01-24 13:22 |  | Norican | 21600 | PD23 Week 4-5
Change Request | NORICANSW-178 | 23641 |  | Post go live issues blocker | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Medium | Technical Requirements |  | 2023-01-24 13:05 | 2023-01-24 13:07 |  | Norican | 72000 | PD23 Week 4-5
Change Request | NORICANSW-177 | 23640 |  | D365FO upgrade: Database upgrade | Bjarne Mortensen | 557058:0534088c-1ed7-4fd0-9fb8-c6c81d5e944f | Bjarne Mortensen | 557058:0534088c-1ed7-4fd0-9fb8-c6c81d5e944f | Medium | Ready For Dev |  | 2023-01-24 12:57 | 2023-01-24 13:18 |  | Norican | 28800 | PD23 Week 6-7
Epic | NORICANSW-176 | 23639 |  | D365FO upgrade |  |  | Bjarne Mortensen | 557058:0534088c-1ed7-4fd0-9fb8-c6c81d5e944f | High | Open |  | 2023-01-24 12:40 | 2023-01-24 21:01 |  | Norican
Change Request | NORICANSW-175 | 23638 |  | D365FO upgrade: Interconnect | Bjarne Mortensen | 557058:0534088c-1ed7-4fd0-9fb8-c6c81d5e944f | Bjarne Mortensen | 557058:0534088c-1ed7-4fd0-9fb8-c6c81d5e944f | Medium | Ready For Dev |  | 2023-01-24 12:30 | 2023-01-24 13:18 |  | Norican | 7200 | PD23 Week 6-7
Change Request | NORICANSW-174 | 23621 |  | 008742 PreApprove rules | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Highest | Stakeholder Sign-off |  | 2023-01-23 11:59 | 2023-01-27 09:15 |  | Norican | 14400 | PD23 Week 1-3 | PD23 Week 4-5
Change Request | NORICANSW-173 | 23618 |  | 008722 Job to approve D_xxxx IDs | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | Mads Granding | 557058:fd044a13-e124-40e7-a31e-8f221f186099 | High | Ready For Dev |  | 2023-01-23 09:20 | 2023-01-30 09:05 |  | Norican | 10800 | PD23 Week 1-3 | PD23 Week 4-5
New Feature | MOTUSSW-29 | 23637 |  | Migration tools move from historical work area 2.0 fix | Per Nielsen | 5f9bc93081b2880078c8e8b3 | Dung-Phuong Thi Hoang | 611a61aac2f3a50069d13443 | Highest | Stakeholder Sign-off |  | 2023-01-24 11:44 | 2023-01-26 11:10 |  | Motus | 27000
Change Request | MGAESW-186 | 23644 |  | Item Coverage Groups | Alex Trask | 61f14ecb9e8939006916f2b6 | Rick Trask | 5ede4ba896beaa0aaef74e58 | High | In Progress |  | 2023-01-24 15:11 | 2023-01-28 22:01 |  | MGAE | 36000
Change Request | MGAESW-185 | 23633 |  | BOM Template import to include Valid From and Vaild to dates | Alex Trask | 61f14ecb9e8939006916f2b6 | Rick Trask | 5ede4ba896beaa0aaef74e58 | Highest | Technical Review |  | 2023-01-23 22:01 | 2023-01-26 21:03 |  | MGAE | 25200
Change Request | HOOKERSW-35 | 23631 |  | Barcode creation for items released to D365 | Alex Trask | 61f14ecb9e8939006916f2b6 | Rick Trask | 5ede4ba896beaa0aaef74e58 | Medium | Technical Review |  | 2023-01-23 20:12 | 2023-01-26 21:03 |  | Hooker | 25200
Change Request | HIGHRESSW-3 | 23689 |  | Add field on Production order with Revision and Hide As Build revision | Jeppe Just Svendsen | 612e36d845cd76006a8913cd | swati amol dhere | 6192355bc15977006af40c1c | High | Estimate |  | 2023-01-26 15:16 | 2023-01-27 12:41 |  | HighRes
Bug | HAWORTHSW-63 | 23707 |  | "E-Con item configuration" on Eng. Object | Jeppe Just Svendsen | 612e36d845cd76006a8913cd | Søren Christensen | 557058:20f5eea0-01b1-45e4-a7cd-fcbfbdf941b8 | Medium | Estimate |  | 2023-01-30 09:22 | 2023-01-30 09:22 |  | Haworth
Change Request | HAWORTHSW-62 | 23677 |  | Econ Variables Update button | Jeppe Just Svendsen | 612e36d845cd76006a8913cd | Søren Christensen | 557058:20f5eea0-01b1-45e4-a7cd-fcbfbdf941b8 | Highest | In Progress |  | 2023-01-26 09:52 | 2023-01-30 09:34 |  | Haworth | 10800 | CR Sprint Week 3-4
Change Request | HAWORTHSW-61 | 23676 |  | Global Valuelist - Where-used button | Jeppe Just Svendsen | 612e36d845cd76006a8913cd | Søren Christensen | 557058:20f5eea0-01b1-45e4-a7cd-fcbfbdf941b8 | Highest | Internal approval |  | 2023-01-26 09:24 | 2023-01-27 11:16 |  | Haworth | 16200 | CR Sprint Week 3-4
Change Request | HAGERSW-3 | 23624 |  | New Fields Requested in the Warranty module | Per Nielsen | 5f9bc93081b2880078c8e8b3 | Tina Trutschel | 6321bfe5d1b3f6489b935228 | Medium | Open |  | 2023-01-23 13:41 | 2023-01-25 13:50 |  | Hager
Change Request | FLORYSW-11 | 23654 |  | Populating Production Order information on the Non-conformance | Rick Trask | 5ede4ba896beaa0aaef74e58 | Rick Trask | 5ede4ba896beaa0aaef74e58 | Medium | Open |  | 2023-01-24 17:15 | 2023-01-24 17:29 |  | Flory
Change Request | DASSW-119 | 23701 |  | User Story 66764: Display product name in the header of the engineering object form | Zhiru Cao | 612e36daa0dfd100689711ce | Janna Ishøy | 623da15aee1b5a00702a0719 | High | Estimate |  | 2023-01-27 13:40 | 2023-01-27 13:42 | 2023-02-10 | DAS
Task | DASSW-118 | 23683 |  | Task 82216: Projects Keywordlist | Zhiru Cao | 612e36daa0dfd100689711ce | Janna Ishøy | 623da15aee1b5a00702a0719 | Medium | Open |  | 2023-01-26 13:19 | 2023-01-26 15:42 |  | DAS
Improvement | DASSW-117 | 23623 |  | Task 81572: Improvement proposal configurator - Upon testing in "test model" show error lines | Jakub Szkandera | 5d6e060b8f0aa30dba0b00f6 | Janna Ishøy | 623da15aee1b5a00702a0719 | High | Estimate |  | 2023-01-23 13:21 | 2023-01-23 21:01 |  | DAS
Bug | DASSW-116 | 23622 |  | Task 82091: Check-in fails for Excel file from Sharepoint | Jakob Bilde Mortensen | 6268ffa0fff19d0069275c72 | Janna Ishøy | 623da15aee1b5a00702a0719 | High | Ready For Dev |  | 2023-01-23 12:55 | 2023-01-26 15:41 |  | DAS | 14400 | PD23 Week 4-5
Change Request | BENNINGSW-46 | 23687 |  | ItemID length validation - max 20 for Items | Jeppe Just Svendsen | 612e36d845cd76006a8913cd | Søren Christensen | 557058:20f5eea0-01b1-45e4-a7cd-fcbfbdf941b8 | Medium | Ready For Dev |  | 2023-01-26 14:39 | 2023-01-30 09:43 |  | Benning | 7200 | CR Sprint Week 5-6
New Feature | BENNINGSW-45 | 23685 |  | Safety relevant BOM Export Report | Jeppe Just Svendsen | 612e36d845cd76006a8913cd | Søren Christensen | 557058:20f5eea0-01b1-45e4-a7cd-fcbfbdf941b8 | Medium | Ready For Dev |  | 2023-01-26 13:40 | 2023-01-30 09:43 |  | Benning | 25200 | CR Sprint Week 5-6
New Feature | BELSW-91 | 23667 |  | Export Engineering Objects with Class attribute values | Zhiru Cao | 612e36daa0dfd100689711ce | Dung-Phuong Thi Hoang | 611a61aac2f3a50069d13443 | Medium | Ready For Dev |  | 2023-01-25 14:20 | 2023-01-27 10:36 |  | BEL | 18000 | CR Sprint Week 5-6

## Products
Product Name | Type | Price | Stock
Toilet Paper | Homesdfsd | 50 | 2001
Hammer | Tool | 40 | 8000
gfgh
gfh | fghgf

## Sheet 1
Column 1 | Column 2 | Column 3
x | 6 | 6
gfhfg

## Sheet 2
Column 1 | Column 2 | Column 3
x | 6 | 6
y | 6 | 6

## Sheet 3
Column 0 | Column 1 | Column 2 | Column 3
Cell 0 | Cell 1 | Cell 2 | Cell 3

## Sheet 4
Column 0 | Column 1 | Column 2 | Column 3
Cell 0 | Cell 1 | Cell 2 | Cell 3

## Sheet 5
Column 1 | Column 2 | Column 3 | Column 4

## Sheet 6
Column 1 | Column 2 | Column 3 | Column 4

## Sheet 7
Column 1 | Column 2 | Column 3 | Column 4

## Sheet 8
Column 1 | Column 2 | Column 3 | Column 4

## Sheet 9
Column 1 | Column 2 | Column 3 | Column 4

## Sheet 10
Column 1 | Column 2 | Column 3 | Column 4

## asdasd
Column 1 | Column 2 | Column 3 | Column 4